## Wave Ownership Matrix
Wave | Ticket ID | Owner | Area | Depends On | Primary Exit Criteria
Wave 0 | CRM-REC-104 | Agent B | Investigation | None | 12710 documented as duplicate / legitimate / unresolved
Wave 0 | CRM-REC-102 (inventory) | Agent B | Legacy flex inventory | None | Legacy FLEX-* and orphan .N rows inventoried with examples
Wave 1A | CRM-RS-101 | Agent A | Change Start Date | None | Current and New Schedule Date columns displayed inline
Wave 1A | CRM-RS-102 | Agent A | Change Start Date | CRM-RS-101 | Live collision detection and plain-English row-level errors
Wave 1A | CRM-RS-103 | Agent A | Change Start Date | CRM-RS-102 | Apply disabled whenever any collision exists
Wave 1A | CRM-RS-104 | Agent A | Change Start Date | CRM-RS-101/102/103 | Two-column layout and persistent Date shift preview complete
Wave 1B | CRM-REC-105 | Agent B | Reconciliation foundation | None | Match-group metadata persists resolution type and created/affected ids
Wave 1B | CRM-REC-101 | Agent B | Reconciliation foundation | CRM-REC-105 recommended | No flex child persisted during preview or option selection
Wave 1B | CRM-REC-110 | Agent B | Adjustment ledger | None | Odd-amount / multi-unit adjustments stored as total-dollar ledger entries
Wave 2 | CRM-REC-106 | Agent C | Scenario A | CRM-REC-105, CRM-REC-110 | Single-schedule adjustment flow works and leaves price_each unchanged
Wave 2 | CRM-REC-107 | Agent C | Scenario B | CRM-REC-105, CRM-REC-110 | Current + future adjustment flow works and explicitly includes 12699
Wave 2 | CRM-REC-108 | Agent C | Scenario C | CRM-REC-105, CRM-REC-101 | Child flex schedule created only on confirm in [parent].[sequence] format
Wave 2 | CRM-REC-109 | Agent C | Shared UX/copy | CRM-REC-106/107/108 | Step 2/3 copy matches March ledger wording across A/B/C
Wave 3 | CRM-REC-103 | Agent D | Undo / reversal | CRM-REC-105, CRM-REC-106/107/108 | Undo deletes only artifacts owned by the same match group
Wave 3 | CRM-REC-102 (cleanup) | Agent D | Cleanup | Wave 0 inventory, CRM-REC-103 | Cleanup dry-run report produced before live mode
Wave 3 | CRM-REC-104 (follow-through) | Agent D | Suppression follow-through | Wave 0 investigation proof | 12710 suppressed only if duplicate status is confirmed